## Sheet1
No. | Risk | Description | Low/High Quality Problem | Impact (A) L = 1 M = 3 H = 5 | Probability (B) L = 1 M = 3 H = 5 | Risk Index A X B | The Problems Caused by Specific Circumstances | Rank | Mitigation Method
1 | User may not understand how the website works | For first timers especially since an program advisory generator tool is uncommon, user might face diificulties understanding the program or how it used | Low | 1 | 3 | 3 | User will not be able to make full use of the website and outcome of results might not satisfy user. | 5 | A video on how to use the website embedded in hte landing page of the website, will act as a tutorial for users to easily follow and understand how the website works
2 | User may select the wrong program | The risk in this section is that the user may select the wrong program, which can lead to undesired program pathway. | High | 5 | 3 | 15 | The user's educational route may be significantly impacted by choosing the improper program, which may result in inaccurate course selections. | 3 | Provide complete and details guidelines for choosing a program. Verify that the dropdown menus function properly by testing them.
3 | Accidental actions | User may accidentally click on certain buttons they did not intend to click such as the reset button | Medium | 3 | 3 | 9 | User would end up removing their progress by accident and have to take the time to restart again | 4 | Prompt confirmation for users of their selection (e.g. reset button)
4 | User can only have one pathway choice at a time | The pathway generator allow user to create and store only one pathway and user will not be able to compare the pathways on the website. The only way is to edit and reset | Medium | 5 | 5 | 25 | User may find the website troublesome as they have to re-edit the pathway to view various pathway options and remember the pathways they have generated to compare the options in their mind | 2 | A way to do this is to allow a few pathway storage, allowing user to compare at least 2 selected pathways at a single time
5 | Once the pathway has been reset, user will have to create it from scratch | The website currently does not have options to save the pathway they have created (e.g pdf, jpeg) and the only way is to take screenshots or pictures of the website | Medium | 3 | 5 | 15 | User may find it troublesome to take partial screenshots of the entire pathway which is time consuming as user will need to scroll part by part of the website | 1 | A way to settle is to allow the pathway to be saved as a pdf or other suitable formats